## Sheet1
Graphical Enigma Simulator
Majed Monem
Supervisor | Prof. John Arnott
Minutes of meetings
Date | Time
2014-09-05 | 11:30
Which programming language to use?
Brief Discussion
Introduction to project
Good Initial Discussion with Prof. Arnott
Good idea to choose Graphics module!
2014-10-08 | 11:30
C++ will be used
Background reading
One rotor to start with - like a prototype#
Maybe 3 if time
Cryptomuseum.com
Look for Enigma simlators online
Graphical representation, 3D?
Maybe attack maethod to guess cipher text
Requirements
2014-10-15 | 11:30
The system shall unscramble cipher text to plain text
Attach method - encrypted plain text
Decryption requirements
Reference book titles
Intro and background of final report
Refine requirements
Gantt chart
Minutes of meetings!
Prototype sketches
Specification and design
2014-10-22 | 11:30
The Hut 6 book - good bg info
Send github link
Specification requirements
Prototypes
2014-10-28 | 13:00
Spelling error in report!
Encrypt rotor types
Move on current letter being deciphered
26x26x26 - find out information
1 use case document
Start ethics!
2014-11-04 | 13:00
Reviewed ethics with Prof. Arnott
All Enigma capital E!
Change app/program to simulator!
Can also decrypt during testing
Demographic questionnaire - who?
Change group to I
Staff member
70 -> 60
must -> should
Give feedback to participants
Look at #7
Infosheet diag tool -> simulator
John's email
project -> simulator
product -> simulator(SUS)
Align - agree/disagree
Specs | Another draft for next week
Just before War polish broke enigma code
Reviewed Specification requirements
Try finish use cases
2014-11-11 | 13:00
Review 2nd draft of ethics
Comparing? No times - feedback
Should know which outcomes of evaluation questionnaire is
No '@' symbol on John's email - fix
Submit ethics
2 questionnaires not 1
Use case change player to user (exit)
Change all of exit to match simulator!
Start UI?
Continue BG on report
2014-11-18 | 13:00
Letters to light up?
Plugboard?
Start Developer - UI
2014-11-25 | 13:00
Ethics Approved!
2014-12-03 | 12:00
Do some work over holidays!
Will get emailed about next meeting
2015-01-20 | 12:00
Put 2:1 for mid-term report
Tooltips? When user hover overs parts?
Add plugboard at end?
2015-01-27 | 13:00
Showed progress of work done
Change viewpoint?
Get wires working!
2015-02-03 | 12:00
Wires completed!
Wires to glow -yes!
Currenet path
Add reflector
Both, button and live action?
2015-02-10 | 12:00
Stick to one rotor - finish one rotor!
Have block for reflector?
As long as you can see current going in to reflector
Decryption! Then reflector maybe?
2015-02-20 | 16:00
Decrypt working!
Need only to show current passing back to decrypted letter
Different reflector and key rotor
Green and red wires
Need to start testing soon
Bring laptop to show
show what the current key is?
2015-02-25 | 13:00
Shown work done
Labels on components maybe
Help and info section explained that this is with one rotor
Testing - does this work? (angle as well of camera)
So does A cipher to X?
Reflector wire!
2015-03-03 | 12:00
Don't need to fix decrypt
If A 26 time, should come back, should come back not as A!
Bug report
Improve UI
Write test strategy
10 people for evaluation
2015-03-10 | 12:00
Cross over wire in reflector
Make reflector stuff rotate
Explain process - why green and red
Tweak interface and components
Test plan - include in appendix
2015-03-17 | 12:00
Testing complex
Start Evaluation
Work on report
2015-03-25 | 13:00
Evaluation done
Write about 3 rotor in future work
Add appendices
2015-03-31 | 12:00
Done Evaluation summary
2015-04-29 | 11:45
Project about develop educational tools
Illustrate Enigma
Make very clear how letter working
Reflector
what I learnt.